## Slide 1
MIGRATION FRAMEWORK

## Slide 2: Cloud Migration Process - Stages
Discovery
Pre -Implementation
Implementation
Test-Validation
Handover
Design
BAU
Assessment
Migration Process (Infra-Level)
Assumptions:
1. Infra Discovery is already performed with help of:
Requirements from Customer’s BU’s for target workload
Tool based discovery with CMDB from ServiceNow, VMRA tool, MAP Toolkit, different SAS toolkits for discovery & automated dependency mapping
Questionnaires & Stakeholder interviews
2. Cloud Assessment is already completed with help of:
Discovery Phase Output
Cloud Assessment tools like Cognizant Cloud Steps
Questionnaires & Stakeholder interviews
App Portfolio based on BU’s
BOM’s
Move Groups Decision
CAT Team (Major)
Cloud Delivery Team (Major / Minor)
Cloud Delivery Team (Major)
Infra Security Team (Major)
BAU Support Team (Major)
Notes:
Detailed Discovery & Assessment are sometimes done by Cloud Delivery Team along with Infra-team & customer’s stakeholders - A Team Activity
Sometimes during BAU, there might be need of developmental support, where cloud-team can complement the support activities (not being in shared mode)

## Slide 3: Cloud Migration Process- Overview
Discovery
Pre -Implementation
Implementation
Test-Validation
Handover
Design
BAU
Assessment
Discover the infrastructure & Identify Preliminary Workload
Analysis to define the high level scope & Requirements for Migration
Define & Finalize Architecture (Infra/Network/Security/Sizing/Capacity Planning)
Environment Preparation – Basic Infrastructure & Pre-Requisites for Implementation to Start. POC to validate Migration Approach
Start creating VM
Foundation Setup
Deep-Dive Planning
Deep-Dive Analysis
Identify
Ready to Build
Testing
KT & Sign-Off
Signed Off & Exit
Validate your Setup & Fix Issues aligned to customer’s requirements
Provide KT with SOP documents
CMDB
High-Level Migration Approach
Detailed Migration Approach & Design Documents
Subscription Setup, Basic Infra, Migration Approach Validation
Migrate VM based on Design
SOP + Test-Plan
SOP
Test Plan

## Slide 4
DESIGN

## Slide 5: Design
Design
Network Topology Analysis
Capacity Planning
Core Architecture decision
Subscription management
Security
Tool Evaluation
Migration Approach Finalization
Test Plan

## Slide 6
Design-Network Topology Analysis
Hybrid connectivity
  Site-to-site VPN:- IPsec tunnel based connectivity over the public internet
  Express Route :-Private ,low-latency and dedicated bandwidth
Region
  Factors to be considered like latency ,connectivity , proximity & compliance
Network Decisions
  Factors to be considered like DMZ, Subnet/zoning, IPSec, NSG, LB, DNS
Security/Defense
  Factors to be considered like DDoS Protection ,Azure Security Center, Web Filtering, Anti-Virus
  Intrusion detection/Intrusion Prevention, Firewall, Application Control, Botnet Protection
Inputs :-
  Latency, Resiliency ,Bandwidth Requirements, Security considerations, Type of on premise network device and proximity.
Default
Advanced (Requirement specific)

## Slide 7: Design-Subscription Management
Inputs :-
  Metering & chargeback, Consumption commitment, Access and permission
Subscription Types
  Pay as you Go:- No minimums or commitments. Use credit card to sign-up. Cancel anytime
  Msdn :- Msdn subscription by default gives $150 azure credit every month. It should be used strictly for training and Learning purposes only and not for any workload migrations
  Buy from a Microsoft Reseller :- Cognizant is not buying from resellers as we have an EA. but might be a case in future
  EA :- The Enterprise agreement with Microsoft and vendor for committed invoice .
    EA-Customer: This is an Enterprise agreement procured by customer working with Microsoft
    EA-Cognizant: This is an Enterprise agreement procured by Cognizant working with Microsoft. This option should only be considered if managed services for the workloads hosted in the subscriptions are provided by Cognizant
Default
Advanced (Requirement specific)
Notes: 1) Need to work with Amresh on updating the slide to use CSP instead of Cognizant EA

## Slide 8
Design-Capacity
Region selection
  Cost , compliance and performance.
Azure Compute
  Compute instance sizing as per the resource usage, number of drives and type of storage needed
Azure Storage
  Storage sizing as per IOPS/Throughput requirement, redundancy & cost factor.
  Type of storage needed (Hot/Cold)
Availability requirements
  Provisioning required number of VMs and storage to meet HA and redundancy requirements
Scaling requirement
  VM scaling as per application requirement
HA/DR
  Capacity required for HA and DR setup .
Inputs :-
  Scaling Requirement ,RPO/RTO,SLA,HA/DR, Compute & Data Sizing (IOPS, Throughput, storage types)
Default
Advanced (Requirement specific)

## Slide 9: Design-Security
Network
Native Tools like Windows firewall, NSG, ACL
3rd party firewalls from azure market place like Barracuda, Netscalar, Fortinet, Trend Micro etc.
DDoS prevention and network boundaries by VLAN segregation will be used different type of workloads, like PROD, DEV, TEST, Apps, DB
Infrastructure
VM :-OS hardening, Antivirus, Vulnerability Scan ,ACL, SSL
OS patching on regular interval
Data:- Azure Storage Encryption, Key Management, Disk Encryption, SAS, Data masking
Identity Management
Azure AD implementation
RBAC :- Role based restriction to services/resources
AD authentication, ADFS and SSO will be evaluated to use
Compliance
General compliance requirements specific to region, data or type of industry
Logging
Logs – Activity logs, log retention, log analytics,
Inputs :-
  Security requirements for Network, Data, Identity Management ,Infra
Default
Advanced (Requirement specific)

## Slide 10: Design-Tool Evaluation & Validation
Native Azure Tools
Infra provisioning :- ARM Template, PowerShell
Monitoring :- Azure Monitor,Native metrics, Application Insights, Azure OMS
Governance:- RBAC
Data transfer :- Azcopy/Robocopy, Azure Import export service, Storsimple, rsync, smb-mount
VM migration and DR :- ASR
Elasticity :- VM Scale set
Schedule tasks:- Run book
Backup & Recovery :- Back Vault, Recovery Vault
Cognizant Tools
Automation :- Reusable Solution and Frameworks
Monitoring :- Cloud 360
Orchestration :- Zennoss
3rd party
Automation:- Terraform, Rightscale
Data transfer :-Aspera, Winscp, Tsunami UDP, Cloudberry, Storage Explorer, Etc.
Security :Barracuda WAF and Network Firewall, NetScalar, Nessus, Symantec, Trend Micro
Monitoring :- New Relic, Nagios
Load Balancer :-F5,A10,Citrix,Kemp
Governance:- HanuInsight, Existing on-premise tools
Based on Tool-Evaluations with POCs:
  Create migration strategy, OR
  Revalidate and update the Initial proposed Migration Strategy (as part of design)
  for individual solution components
Seek help from Microsoft for review on each approach and design proposed
Default
Advanced (Requirement specific)

## Slide 11: Design-Core Architecture
Architecture Design
Deployment architecture
Environments (Prod/Non-Prod/Lower environments)
Security
TCO
HA/DR
Backup
Containerization
Compliance
Agility
Legacy applications and servers
DevOps
Inputs :-
  Financial requirements, Performance Metrics, RPO/RTO,SLA, Back up requirement ,Security Requirements ,Other NFR
Default
Advanced (Requirement specific)

## Slide 12: Design-Test Plan
Infra Test Plan
Network Connectivity Test Plan
VM Accessibility Test Plan
Security Test Plan
HA / DR Test Plan
Backup & Recovery Test Plan
Inputs :-
  Design of each solution components
Default
Advanced (Requirement specific)

## Slide 13: Design-Artifacts
Artifacts
  Design guidance
  Project learnings
  White papers
  Point of Views
  Reference architectures
  Best practices
Default
Advanced (Requirement specific)

## Slide 14
Pre-Implementation

## Slide 15: Pre-Implementation
Pre-Implementation
Subscription setup
Foundation setup
Migration readiness

## Slide 16: Pre-Implementation-Subscription setup
EA Agreement
  Cognizant EA:- Submit the form to the ITRMG team to department and account creation
  Customer EA:-Customer to create the departments, account and subscription .Provide the access to subscription
AAD Setup – (PS script explore - WAP) – Q2 2017
  Create AAD
  Add and configure Domain
  Download and setup AD Connect
  Password sync
  ADFS setup
Admin Setup - (PS script explore - WAP) – Q2 2017
  Create/manage Account owners
  Create subscription and provide access to subscription
  Setup accounts to view billing and invoice details
RBAC - (PS Scripts) – Q1 2017 – Feb 2017
  Create resource groups
  Create custom RBAC roles or reuse Azure provided RBAC roles
  Create groups and users and assign them to roles and resources
Default
Advanced (Requirement specific)

## Slide 17: Pre-Implementation-Foundation Setup
Storage accounts
  Create and setup storage account with agreed redundancy (Create through Terraform) , (PS Scripts)- Completed..
Network
  Setup Virtual Network, Subnets & NSG (Create through terraform) , (PS Scripts) – Completed..
  Procurement & Setup of Express Route / S2S - (PS Scripts WAP) - Yet to start..- need solution track
Golden Image
  OS hardening – (Enables using Chef / Puppet tools) – WIP - (Q1 2017) - Jan 2017
  Anti-virus Installation – (Popular agents cookbooks/ recipes if applicable to be captured in Reusable Library..) (Q1 2017) – Mar 2017
  VHD Setup (Enables through Packer, Chef and Puppet Tools) – WIP – Chef & Puppet Automation track( Q1 2017) – Feb 2017
  Framework & Tools Installation
  Additional Configurations
Automation
  Creation of reusable assets using ARM, Terraform, PowerShell, Chefs & Puppet
Default
Advanced (Requirement specific)

## Slide 18: Pre-Implementation-Foundation Setup
Identity Management
  AAD Setup
  Windows AD Setup – Yet to start – Q2 2017
  AD Connect & Dir Sync – (PS Script)- Yet to Start – Q2 2017
  Domain Controller – (PS Script) – Yet to Start – Q2 2017
  Domain Setup – (PS Script) Yet to Start – Q2 2017
  AD HA Setup – (PS Script) Yet to Start – Q2 2017
Default
Advanced (Requirement specific)

## Slide 19: Pre-Implementation-Migration Readiness
POC
  Backup & Recovery Vault
  RoboCopy
  StorSimple
  Import/Export
  AzCopy
  POC’s on 3rd party tools considered during the design phase
Default
Advanced (Requirement specific)

## Slide 20: Pre-Implementation-Artifacts
Artifacts
  Reusable Foundation Provision Scripts
  Reusable Foundation Validation Scripts
  Learnings on POC ( reusable KR)
  Foundation Documentation template
  CMDB on Azure
  Best Practices – The document uploaded in SharePoint and location is Azure Standard.
Default
Advanced (Requirement specific)

## Slide 21
Implementation

## Slide 22: Implementation
Implementation
VM Setup & Configuration
Back-up & Recovery
Network & Firewall Setup

## Slide 23: Implementation- VM Setup & Configuration
Workload VM Setup
  Provision VM through automation scripts (PS Scripts/Terraform/ARM Templates) - Completed
  Create and attach disk (PS Scripts/Terraform/ARM Templates) – WIP (Chef & Puppet track )– Q1 2017 – Jan 2017
Workload VM Configuration
  Join the provisioned VM’s to the domain as required (Enables through Chef) , (PS Scripts) - Completed
  Setup user access permissions
  Setting up workload specific features/ Software like Apache Tomcat, Oracle etc. (Enables through Chef) – (Reusable Library)
  Install/ enable OS level features and services based on the agreed design and requirements like AD, DNS,IIS, etc. - (PS Scripts - WAP) – (Reusable Library)
  Configure clustering
  Configuring HA - (ARM) – WIP – Q1 2017 – ( Reusable Library) – Feb 2017(SQL HA)
  Installing App Specific Agents
  Infra Appliances Setup
  Setup own appliances or procure from marketplace - (Reusable Library)
  Setup security appliances like Barracuda WAF, NetScalar, Symantec,Trend Micro etc.. as per design - (Reusable Library)
  Setup Monitoring tools like Cloud 360,Zenoss, New Relic, Nagios etc.. as per design - (Reusable Library)
  Setup Load Balancer appliances like Azure Load balancer F5,A10,Citrix,Kemp etc as per design - (Reusable Library)
Default
Advanced (Requirement specific)

## Slide 24: Implementation- Network & Firewall Setup
Network & Firewall
  Create app specific NSG and ACL’s (Enables through Terraform) (PS Scripts) – WIP(Terraform)/Completed(PS Scripts) – Q1 2017- Jan 2017
  Setup Routing tables (PS Scripts) - Completed
  Setup Firewall rules
  Enable RDP/SSH port and rule for windows and Linux respectively for connecting VM securely through remote site
  Setup DNS rules
  Configure Load balancers ILB and External ILB (Enables through Terraform), (PS Scripts)- WIP – Q1 2017 – Terraform Jan 2017/ March 2017
  Configure security firewalls
  Configure DMZ access rules
  Setup/Configure Traffic Manager (Enables through Terraform), (PS Scripts) – yet to start – Q2 2017
Default
Advanced (Requirement specific)

## Slide 25: Implementation- Backup &Recovery
Configure Backup
  Setup backup tools like Azure backup, Vault, DPM etc. as per agreed design(PS/ ARM)- WIP – Q1 2017 – Mar 2017
  Install backup agents as required on the VM (PS Scripts) - Completed
  Configure Retention policies as per requirement (PS Scripts) - Completed
  Configure backup schedule as per SLA’s
  Need for data compression and encryption at rest
  Backup at DB and application layer
  Hot/Cold backup – (PS Scripts) – Yet to Start- Q2 2017
  Environments and servers to be backed up
Configure Recovery
  Setup recovery tools like Site recovery etc.. As per agreed design(PS Scripts) – Completed..(Need to check with Suhas)
  Setup Disaster recovery instances and configuration
  Create and test recovery scripts
  Simulate DR and Validate the Setup
  RTO/RPO considerations
Default
Advanced (Requirement specific)

## Slide 26: Implementation-Artifacts
Artifacts
  Build/Provision scripts
  CMDB on Azure
  Backup & Recovery ( documentation of backup and recovery strategy and implementation for BAU Handover)
  Security documentation ( documentation of security rules, firewall rules and additional security details)
  Infra validation Scripts
  Best Practices
Default
Advanced (Requirement specific)

## Slide 27
Test/Validation

## Slide 28: Test/Validation
Test/Validation
Network Testing
Monitoring /Reporting
Infra Testing
AD Testing
Work Load Testing

## Slide 29: Test/Validation – Network Testing
Validate Connectivity ( no scripts created for any kind of testing for now, need to discuss, explore and create)
  Validation of connectivity to resources like VM NIC, subnet, vNet etc. between cross premises
  Validation of latency and connection speeds
  Validation of redundancy setup for resiliency
  Validation of recovery setup if any
Validate Security Setup
  Validation of NAT rules
  Validation of inbound and outbound rules ( NSG)
  Validation of priorities of rules
  Validation of ACL’s and Firewall rules
  Penetration testing
  Validate 3rd Party appliance Setup
Validate DNS Setup
  Name resolution testing
  Nslookup
  Validation of Zones
Default
Advanced (Requirement specific)

## Slide 30: Test/Validation – AD Testing
Windows AD on cloud
  Recommended configuration DCs in cloud
  Resilient functionality without on premise connectivity
  Validate bi-directional data sync
Azure AD
  Validate authentication from native and web applications
  Validate Kerberos & NTLM in case of ADDS
  Validate unidirectional / bi-directional data sync
  Validate all supported OAuth workflows and protocols (if applicable)
  Validate MFA (if applicable)
  Federation (if applicable)
    Recommended configuration and functioning of Federation endpoint
    Validate that MFA is setup and works as expected (if applicable)
Default
Advanced (Requirement specific)

## Slide 31: Test/Validation-Monitoring /Reporting
Monitoring & Reporting
  Validate monitoring parameters
  Validate Alert Triggers
  Validate Notification messages
  Validate data flow to reporting and monitoring tools of customer (If any)
  Validate data flow to reporting and monitoring tools of Zenoss/C360
  Validate data flow to OMS
  Validate data flow in to SCOM
Default
Advanced (Requirement specific)

## Slide 32: Test/Validation- Infra Testing
Infra Validation
  Validate basic details like Naming conventions, additional disc information,
  Validate VM’s Domain join
  Validate if Patch management is applied correctly
  Validation of Security parameters
  Stress, Load and Performance testing ( Disk ,CPU ,Network, Latency)
  Validate backup setup and configuration
  HA/DR testing
  Backup and restore validation
Default
Advanced (Requirement specific)

## Slide 33: Test/Validation-Workload Testing
App Validation
  Functional testing
  Data configuration and consistency validation
  NFR validation
  Integration testing
  Security Testing
  Validate Application Monitor Parameters
  DevOps validation (CI & CD)
  HA/DR testing
  Cluster Replication validation
  Performance Testing
Default
Advanced (Requirement specific)

## Slide 34: Test/Validation-Artifacts
Artifacts
  Test plan
  Test Automation Scripts
  App validation Scripts
  Integration Testing Scripts
  NFR Validation Testing ( RTO,RPO, Performance… validation document)
  Monitoring & Reporting validation (List out all the parameters and produce a validation document for a business sign-off)
  Best Practices
Basic (Minimum)
Advanced (Requirement specific)

## Slide 35
Handover

## Slide 36: Handover
Handover
Knowledge/Capability Alignment
KT/Demos
Documentation

## Slide 37: Handover
Knowledge/Capability Alignment
  Identify the resource with right skills, in case of support for developmental activities. E.g. Azure-script-maintenance. If no resource to support such activities, acknowledge the cloud delivery management for resolution
Documentation
  Prepare and Provide the all set of handover documents specific for environment ,back up & recovery ,DR data sync ,User access and critical technical challenges faced.
  Learning section for Azure services utilized in the project
KT/Demos
  Provide the all set of Demo’s and KT
Default
Advanced (Requirement specific)

## Slide 38: Handover-Artifacts
Artifacts
  KT documentation
  BAU Scripts ( if any)
  Demos
Default
Advanced (Requirement specific)

## Slide 39
CCS Architecture Team